## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Team 9: Music Matters Booking | [6 empty] | Completed | 1
| Team Members: | Byron Prather, Quinterious Hall, Jesse De Melo | [6 empty] | Discarded | 2
| Date: | 2021-11-02 | Cycle: | 3 pt 1 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | We want to design a web application booking system that allows a user to record and display artist names, performance times, dates, and locations, in an interactive calendar format. As well as finish the iOS application. | [6 empty] | In Review
Unstarted
| Cycle Intent: | The intent for this cycle is to begin hard coding for the website, designing the calendar feature and the automatic emailing function.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Ease of Use |  | 1 | 6 | 2 | Collaboration | 2 | 6
2 | Intuitiveness |  | 1 | 4 | 0 | Completed | 0 | 4
3 | Data Transfer Reliability |  | 1 | 6 | 6 | Unstarted | 0 | 6
4 | Database Data Synchronization |  | 2 | 8 | 6 | Collaboration | 2 | 2
5
|  |  | Planned Total | 24 | 14 | Actual Total | 4 | 18

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Team 9 Music Matters Booking
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Byron Prather | 4 |  |  |  | 6 | [8 empty] | 0 | 0
| Quinterious Hall | [13 empty] | 0 | 0
| Jesse de Melo | [13 empty] | 0 | 0
[15 empty] | 0 | 0
[5 empty] | Totals | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Byron Prather: Created wireframe, waiting for sponsor approval. | [6 empty] | Begin coding front end of website and prepare for back end coding.
| Obstacles encountered since last status report: | [6 empty] | Notes:
None so far
Risks facing the project:
Lorem ipsum dolor sit amet, consectetur adipisicing elit, sed do eiusmod tempor incididunt ut labore et dolore magna aliqua. Ut enim ad minim veniam, quis nostrud exercitation ullamco laboris nisi ut aliquip ex ea commodo consequat. Duis aute irure dolor in reprehenderit in voluptate velit esse cillum dolore eu fugiat nulla pariatur. Excepteur sint occaecat cupidatat non proident, sunt in culpa qui officia deserunt mollit anim id est laborum.

## Member 1 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Team 9 Music Matters Booking
Member: |  | Byron Prather
Week Ending:
Cycle: |  | Cycle 3 pt 1
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Worked on Cycle 3 pt 1 report
Date: | 2021-11-02 | Result: | Report ready for teammates to add onto.
Hours Worked: | 1 | Problems encountered: | Using github to transfer files for multiple people to work on can be slow.
Day: | Monday | Task(s) performed: | Learning how to create a user interface that can upload data to firebase.
Date: | 2021-11-01 | Result: | Preliminary Interface Programmed
Hours Worked: | 3 | Problems encountered: | It does not look good visually appealing.
Day: | Tuesday | Task(s) performed: | Continued to tinker with interface for firebase uploading.
Date: | 2021-11-02 | Result: | Further Development on interface
Hours Worked: | 2 | Problems encountered: | Not visually appealing, and struggling to get with Radio element for boolean inputs.
Day: | Friday | Task(s) performed:
Date: | 2011-12-28 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2011-12-29 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2011-12-30 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2011-12-31 | Result:
Hours Worked: | ? | Problems encountered:

## Member 2 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Team 9 Music Matters Booking
Member: |  | Quinterious Hall
Week Ending:
Cycle: |  | Cycle 3 pt 1
Team Member Work Summary
Monday | Thursday | Task(s) performed: | Debugged issues with Expo and Apple Developer Portal communication/authentication.
Date: | 2021-09-16 | Result: | Expo is authenticated with Apple Developer and ready for upload into TestFlight.
Hours Worked: | 5 | Problems encountered: | Proper credentials were not created for the team Expo account to be used with Apple Developer, causing repeated failures.
Day: | Friday | Task(s) performed: | Make a new build in TestFlight since the previous build has expired
Date: | 2021-09-17 | Result: | Build failed and app still is expired in test flight.
Hours Worked: | 3 | Problems encountered: | New build could not be produced due to new error with Apple Developer and App Store Connect
Day: | Monday | Task(s) performed: | Added myself as a trusted user in App Store Connect
Date: | 2021-09-20 | Result: | Now have access to data about builds and can debug issue with TestFlight upload better with access to app information.
Hours Worked: | 2 | Problems encountered: | No problems have been encountered with this specific task.
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:

## Member 3 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Team 9 Music Matters Booking
Member: |  | Jesse De Melo
Week Ending:
Cycle: |  | Cycle 3 pt 1
Team Member Work Summary
Day: | Saturday | Task(s) performed: | Conduted a research to find ways to implement an interactive calendar that the Sponsor can use to schedule and display music booking appointments.
Date: | 2021-09-18 | Result: | Found a way to do this implementation using Javascript Vue framework along with Vuetify and Firebase to be able to store the appointments in the database.
Hours Worked: | ? | Problems encountered: | No problem encountered at the moment. I am currently prototyping for the implementation of this component of the website.
Day: | Wednesday | Task(s) performed:
Date: | 2011-12-26 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2011-12-27 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2011-12-28 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2011-12-29 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2011-12-30 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2011-12-31 | Result:
Hours Worked: | ? | Problems encountered:

## Member 4 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | YOUR PROJECT NAME
Member: |  | YOUR NAME
Week Ending: |  | INSERT DATE HERE
Cycle: |  | SPIKE, CYCLE 1,2, or 3
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Worked on thigamajig. Integrated the sprocket with the cog. Developed a test plan for the widget.
Date: | 2011-12-25 | Result: | Thigamajig completed and ready for unit testing. Sprocket and cog integration 65% complete.
Hours Worked: | ? | Problems encountered: | Sprocket and cog don't fit together correctly. A kotter pin might be required to hold the cog in place.
Day: | Wednesday | Task(s) performed:
Date: | 2011-12-26 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2011-12-27 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2011-12-28 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2011-12-29 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2011-12-30 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2011-12-31 | Result:
Hours Worked: | ? | Problems encountered: